## Slide 1
PREPARED FOR OUR VENUE PARTNER
THE FULL
GAME PLAN
Schedule, prompt, judging, food, and cleanup. Every detail of Falcon Hacks ’26, start to finish.
SAT NOV 7, 2026 · 8:00 AM – 8:30 PM · 150 HACKERS
Abhinav Garg, Founder · Falcon Hacks

## Slide 2
01 · AT A GLANCE
The event in numbers.
150
hackers in 50–70 teams of 2–4
12.5 HRS
8:00 AM doors to 8:30 PM close
8.5 HRS
of building time, prompt to code freeze
$4,000+
raised · ElevenLabs, VitalEdge & more
FREE
every attendee: food, prizes, no ticket
7–12
judges working in panels of 2–3
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 3
02 · THE DAY, MINUTE BY MINUTE
Schedule.
7:15 AM
Organizers and volunteers arrive. Tables, signage, check-in, A/V set up.
8:00 AM
Doors open. Check-in, name tags, team tables. Light breakfast snacks.
8:45 AM
Kickoff. Welcome, rules, sponsor intros (ElevenLabs, VitalEdge, YRI, ArgosX & more).
9:00 AM
Prompt revealed live. Hacking begins — 8.5 hours on the clock. Fresh repos only.
12:30 PM
Lunch — Costco pizza. Mentors keep circulating.
5:30 PM
Code freeze. Submissions in by 5:45: repo link, 100-word blurb, and a screenshot.
5:45 PM
Dinner — Panda Express. Judges preview every submission while teams eat.
6:15 PM
Judging begins in the private judging room. Teams called in on a posted order.
7:45 PM
Top 6 demo on stage, 3 minutes each, whole room watching.
8:15 PM
Awards. 8:30 PM doors close. Venue clean and empty by 9:00 PM.
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 4
03 · THE PROMPT
The prompt.
Prompt revealed at kickoff — locked with venue partner.
The final prompt is being decided with our venue partner and stays sealed until 9 AM on event day. It will be a technical prompt that no team can prepare for in advance and every skill level can build on.
Can’t be pre-built
Sealed until the 9 AM reveal, so no one walks in with a finished project. Fresh repos only, started after the reveal.
Fair at every skill level
Chosen so a first-timer can clear it simply and a veteran team can go deep on it. Same bar, same clock, for everyone.
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 5
04 · JUDGING
How judging works.
1 · PREVIEW
5:45 PM
Judges read every submission (blurb + screenshot) over dinner, before they see a single table.
2 · JUDGING ROUND
6:15 PM
Judging happens in a private room, away from the floor. 7–12 judges in panels of 2–3; teams are called in on a posted order. Every team gets the same 3 minutes: 2 to demo, 1 for questions.
3 · SCORE & TALLY
7:30 PM
Panels score on a shared form between teams. Each judge's scores are normalized so a harsh judge and a generous judge count equally, and every score carries a one-line note.
4 · FINALS
7:45 PM
Top 6 demo on stage to the whole room. Every judge and every attendee sees the same demos.
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 6
05 · THE RUBRIC
Every team, same four questions.
ORIGINALITY
10 PTS
Is this a fresh idea or a re-skin of something that exists? Does it answer the prompt?
EXECUTION
10 PTS
Does it actually work? How much was really built today?
IMPACT
10 PTS
Would someone genuinely use this? Does it solve a real problem?
PRESENTATION
10 PTS
Can the team explain what they built and why?
Scored 1–10 per criterion on a shared Google Form with a one-line note per team. Sponsor awards are scored separately and never touch the main rubric.
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 7
06 · THE FINALS
Top 6, on stage, in front of everyone.
The six highest-scoring teams demo live: 3 minutes each, projected for the whole room. Every judge watches the same demos together, and so does every other team.
WHY IT MATTERS
The room sees exactly what won and why. The teams that didn't win see the bar, not a mystery.
EVERYONE LEAVES WITH SOMETHING
Every project goes in the public gallery. Every participant keeps their ElevenLabs credits, their YRI scholarship, and their project.
AWARDS, 8:15 PM
Overall top 3 from the rubric, plus sponsor awards. Winners' commit history verified before announcement.
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 8
07 · FOOD & LOGISTICS
Fed all day, planned in advance.
8:00 AM
Breakfast snacks
Bagels / donuts + water station (local donations, confirmed week-of)
12:30 PM
Lunch
Costco pizza — 25 pizzas for 150 hackers + volunteers
ALL DAY
Snacks & drinks
Chips, fruit, water refills at a stocked snack table
5:30 PM
Dinner
Panda Express catering trays, served during judges' preview window
Dietary needs are collected at registration and labeled at the food table. Food is budgeted from the $4,000+ already raised.
FALCON HACKS ’26 · EVENT OPERATIONS
falconhacks2026.com

## Slide 9
EVERY DETAIL, ON PAPER, BEFORE THE DAY.
Questions, changes, walkthrough requests — anytime.
Abhinav Garg · abhinavmgarg@gmail.com · falconhacks2026.com